VIZLINT

The Design Quality Gate for AI-Generated Code

────────────────────────────────────────

Sprint Execution Plan

16 Sprints  ·  4 Phases  ·  16 Weeks

Version 1.0  |  March 2026

Confidential — Internal Use Only

# Table of Contents

1. Product Overview & Vision

2. Team Roles & Ceremonies

3. Definition of Done

4. Phase 1: Foundation & Service Launch (Sprints 1–4)

5. Phase 2: Core ESLint Plugin (Sprints 5–8)

6. Phase 3: MCP Server & CI/CD Integration (Sprints 9–12)

7. Phase 4: Dashboard, Teams & Scale (Sprints 13–16)

8. Release Milestones & Revenue Targets

# 1. Product Overview & Vision

Vizlint is the first quality gate built for how code looks, not just how it runs. It validates design quality — spacing consistency, typography hierarchy, color token adherence, responsive coverage, and accessibility — in AI-generated frontend code across any framework.

## Product Pillars

1. Local-First: Zero code leaves the developer's machine. ESLint runs locally. MCP server uses stdio. No cloud dependency.

2. Framework-Agnostic: Works with React, Vue, Svelte, Angular, plain HTML — any Tailwind or CSS-based output.

3. AI-Tool Agnostic: Validates output from Claude Code, Cursor, v0, Bolt, Lovable, Copilot — any AI coding tool.

4. Open Core: Free OSS ESLint plugin for adoption. Paid CLI, MCP server, and dashboard for revenue.

## Tech Stack

Language: TypeScript (everything)

ESLint Plugin: @vizlint/eslint-plugin — AST-based rules via @typescript-eslint/utils

CLI: @vizlint/cli — Commander.js, Chalk, project-wide analysis + Design Health Score

MCP Server: @vizlint/mcp — @modelcontextprotocol/sdk, stdio transport, local execution

Dashboard: Next.js 15 + Tailwind + shadcn/ui (Framer for marketing site)

API: Next.js API routes + Drizzle ORM + PostgreSQL (Supabase)

Monorepo: Turborepo with packages/ structure

CI/CD: GitHub Actions

Hosting: Vercel (dashboard) + npm (packages)

# 2. Team Roles & Ceremonies

Solo founder wearing all hats. Each sprint simulates a full team review cycle:

CEO Hat: Sprint planning, prioritization, business acceptance of deliverables

CTO Hat: Architecture decisions, tech debt management, security review

Solution Architect Hat: System design, integration patterns, scalability review

UX Designer Hat: Landing page, dashboard UI, developer experience

Full-Stack Developer Hat: Implementation, code reviews (self-review via PR)

QA Hat: Test writing, manual testing, edge case validation

McKinsey Consultant Hat: End-of-sprint business review — does this sprint move revenue needle?

## Sprint Ceremonies (1-Week Sprints)

Monday AM: Sprint Planning (1hr) — select stories, define tasks, commit velocity

Daily: 15min standup journal — what did I do, what will I do, blockers

Friday PM: Sprint Review (1hr) — demo deliverables, business acceptance

Friday PM: Retro (30min) — what worked, what didn't, one improvement for next sprint

# 3. Definition of Done

Every user story must meet ALL criteria before marking complete:

- Code written in TypeScript with strict mode enabled

- Unit tests written and passing (minimum 80% coverage for new code)

- Integration tests passing for cross-module functionality

- No TypeScript errors (tsc --noEmit passes)

- ESLint passes on own codebase (dogfooding)

- PR created with description, linked to user story ID

- Self-review completed (CTO hat review checklist)

- Security review for any external input handling

- Documentation updated (README, JSDoc, CHANGELOG)

- Business acceptance: CEO hat confirms story delivers stated value

- McKinsey check: Does this move the product toward revenue?

PHASE 1: FOUNDATION & SERVICE LAUNCH

Sprints 1–4 (Weeks 1–4)  |  Monorepo scaffold, first 5 ESLint rules, productized service live, landing page shipped

Sprint 1: Project Bootstrap & Rule #1

Sprint Goal: Monorepo scaffolded, CI green, first ESLint rule (no-arbitrary-colors) shipping, domain purchased

Velocity Target: 13 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-001: Monorepo & CI/CD Setup

As a developer, I want a properly structured TypeScript monorepo with CI, so that I can develop across packages with confidence

Story Points: 5

Acceptance Criteria:

- Turborepo monorepo with packages: eslint-plugin, cli, mcp, shared

- TypeScript strict mode across all packages with shared tsconfig.base.json

- ESLint + Prettier configured for the monorepo itself (dogfooding from day 1)

- GitHub Actions CI: lint, typecheck, test on every push/PR

- Vitest configured in each package with minimum test scaffolding

- pnpm workspaces configured with cross-package references working

Tasks:

- Initialize Turborepo with pnpm workspaces

- Create package.json for each package with correct cross-references

- Configure shared tsconfig.base.json with strict: true

- Set up Vitest with shared config

- Create GitHub Actions workflow: lint → typecheck → test → build

- Add .nvmrc (Node 20 LTS), .gitignore, LICENSE (MIT for OSS packages)

- Create CONTRIBUTING.md with development setup instructions

Test Cases:

- TEST: pnpm install succeeds from clean clone

- TEST: pnpm build compiles all packages without errors

- TEST: pnpm test runs across all packages (placeholder tests pass)

- TEST: GitHub Actions CI completes green on main branch

- TEST: Cross-package imports resolve correctly (shared → eslint-plugin)

VIZ-002: First Rule: no-arbitrary-colors

As a developer using AI coding tools, I want Vizlint to flag hardcoded color values in my Tailwind classes, so that I maintain consistent brand colors instead of AI-generated arbitrary hex values

Story Points: 8

Acceptance Criteria:

- Rule detects bg-[#hex], text-[#hex], border-[#hex], ring-[#hex] patterns in className attributes

- Rule handles static strings, template literals, cn(), clsx(), cva() wrappers

- Rule provides auto-fix suggestion mapping to nearest Tailwind color (e.g., bg-[#3B82F6] → bg-blue-500)

- Rule is configurable: allowlist specific hex values, define custom color tokens

- Rule reports with clear message: 'Arbitrary color bg-[#FF0000] detected. Use design token: bg-red-500'

- Rule severity configurable: error | warn | off

Tasks:

- Create ESLint rule skeleton using @typescript-eslint/utils RuleCreator

- Implement JSXAttribute visitor for className parsing

- Build Tailwind class extractor handling: static strings, template literals, cn()/clsx()/cva()

- Implement arbitrary color regex: /^(bg|text|border|ring|outline|shadow|accent|fill|stroke)-\[#[0-9a-fA-F]{3,8}\]/

- Build color distance calculator (CIELAB Delta-E) for nearest-token suggestions

- Create rule configuration schema with Zod validation

- Write unit tests for all class extraction patterns

- Write unit tests for color detection and suggestion accuracy

- Add rule to plugin index.ts with recommended config

Test Cases:

- TEST: Detects bg-[#FF0000] in static className string

- TEST: Detects text-[#333] inside cn('text-[#333]', 'p-4')

- TEST: Detects border-[#abc123] inside template literal className={`border-[#abc123]`}

- TEST: Does NOT flag bg-red-500 (standard Tailwind class)

- TEST: Does NOT flag bg-[rgb(255,0,0)] (non-hex arbitrary — separate rule)

- TEST: Suggests bg-blue-500 for bg-[#3B82F6] (exact match)

- TEST: Suggests bg-blue-600 for bg-[#2563EB] (nearest match)

- TEST: Allowlisted hex values are not flagged

- TEST: Rule respects severity configuration

- TEST: Auto-fix correctly replaces arbitrary color with suggested token

Sprint 2: Rules #2–3 & Landing Page

Sprint Goal: no-arbitrary-spacing and typography-scale rules shipping, Framer landing page live at vizlint.dev

Velocity Target: 13 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-003: Rule: no-arbitrary-spacing

As a developer, I want Vizlint to flag hardcoded spacing values like p-[13px] or m-[7px], so that my UI maintains consistent spacing rhythm from the Tailwind scale

Story Points: 5

Acceptance Criteria:

- Rule detects p-[Npx], m-[Npx], gap-[Npx], space-x-[Npx], space-y-[Npx] and all directional variants

- Rule suggests nearest Tailwind spacing scale value (e.g., p-[13px] → p-3 (12px) or p-3.5 (14px))

- Rule handles rem, em, px units

- Rule configurable: custom spacing scale, tolerance threshold for suggestions

Tasks:

- Implement spacing regex patterns for all Tailwind spacing utilities

- Build spacing scale lookup table (default Tailwind 0–96 scale)

- Implement nearest-value calculator with configurable tolerance

- Add directional variant handling (pt, pb, pl, pr, px, py, mt, mb, etc.)

- Write comprehensive unit tests

Test Cases:

- TEST: Detects p-[13px] and suggests p-3 or p-3.5

- TEST: Detects gap-[7px] and suggests gap-1.5 or gap-2

- TEST: Detects m-[2.5rem] and handles rem conversion

- TEST: Does NOT flag p-4 or m-auto or gap-x-2

- TEST: Custom spacing scale overrides work correctly

VIZ-004: Rule: typography-scale

As a developer, I want Vizlint to enforce consistent typography sizing, so that my UI uses a coherent type scale instead of random font sizes

Story Points: 5

Acceptance Criteria:

- Rule detects text-[Npx], font-[N], leading-[Npx], tracking-[Nem] arbitrary values

- Rule suggests nearest Tailwind typography class

- Rule detects inconsistent heading hierarchy (h2 larger than h1 in same file)

- Rule configurable: custom type scale definition

Tasks:

- Implement typography utility regex patterns

- Build type scale lookup (xs through 9xl)

- Implement font-weight arbitrary detection

- Add cross-component heading hierarchy check

- Write unit tests for all patterns

Test Cases:

- TEST: Detects text-[17px] and suggests text-base (16px) or text-lg (18px)

- TEST: Detects font-[450] and suggests font-normal (400) or font-medium (500)

- TEST: Detects leading-[22px] and suggests leading-normal or leading-relaxed

- TEST: Does NOT flag text-sm, font-bold, leading-tight

VIZ-005: Landing Page v1

As a potential user, I want to understand what Vizlint does in 10 seconds on the landing page, so that I decide to try the tool immediately

Story Points: 3

Acceptance Criteria:

- Page loads at vizlint.dev with < 2s LCP

- Hero section: clear headline, 1-line description, install command (npx vizlint)

- Before/after code comparison showing a real detection

- 3 feature blocks: Spacing · Typography · Colors

- CTA: npm install link + GitHub star button

- Footer: GitHub, Twitter/X, MIT License badge

- Mobile responsive

Tasks:

- Purchase vizlint.dev domain

- Set up Framer project with custom domain

- Design hero section with install command snippet

- Create before/after code comparison visual

- Build feature blocks with icons

- Add analytics (Plausible — GDPR compliant, no cookies)

- Test on mobile devices

Test Cases:

- TEST: Page loads under 2 seconds (Lighthouse performance > 90)

- TEST: All links functional (GitHub, npm)

- TEST: Mobile layout renders correctly (320px–768px)

- TEST: Copy-paste of install command works

Sprint 3: Rules #4–5 & npm Publish

Sprint Goal: responsive-required and consistent-component-spacing rules, first npm publish of @vizlint/eslint-plugin

Velocity Target: 13 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-006: Rule: responsive-required

As a developer, I want Vizlint to flag layout components with fixed widths that lack responsive breakpoints, so that my AI-generated layouts don't break on mobile

Story Points: 5

Acceptance Criteria:

- Rule detects w-[Npx] without sm:/md:/lg: responsive variants in same component

- Rule detects fixed-width containers (w-[800px], w-[1200px]) without max-w-* or responsive alternatives

- Rule configurable: minimum breakpoints required (default: sm + md)

- Rule ignores icon/avatar sizing (< 64px) by default

Tasks:

- Implement fixed-width detection for layout containers

- Build responsive variant scanner across className attributes in same component

- Add configurable breakpoint requirements

- Add size threshold for ignoring small fixed elements

- Write unit tests

Test Cases:

- TEST: Flags w-[800px] div without responsive variants

- TEST: Does NOT flag w-[800px] if sm:w-full or md:w-1/2 present

- TEST: Does NOT flag w-8 (32px) for icon containers

- TEST: Configurable breakpoint requirements work

VIZ-007: Rule: consistent-component-spacing

As a developer, I want Vizlint to detect when similar components use different spacing patterns, so that cards, buttons, and inputs have consistent internal spacing across my project

Story Points: 5

Acceptance Criteria:

- Rule analyzes components with similar structure (e.g., all Card-like components) for spacing divergence

- Rule flags when padding/margin patterns differ by > configurable threshold across same-type components

- Rule provides suggestion showing the most common pattern as the 'standard'

Tasks:

- Build component similarity classifier based on JSX structure

- Implement spacing pattern extractor per component

- Build divergence calculator across component groups

- Add threshold configuration

- Write cross-file analysis tests

Test Cases:

- TEST: Detects Card A using p-4 and Card B using p-6 in same project

- TEST: Does NOT flag intentional size variants (CardSm vs CardLg)

- TEST: Reports the dominant pattern as suggested standard

VIZ-008: npm Publish Pipeline

As a developer, I want to install @vizlint/eslint-plugin from npm, so that I can add Vizlint to any project in seconds

Story Points: 3

Acceptance Criteria:

- Package published as @vizlint/eslint-plugin on npm

- Semantic versioning (0.1.0 initial release)

- README with installation instructions, rule documentation, configuration examples

- Flat config (eslint.config.js) and legacy (.eslintrc) support

- GitHub Release created with changelog

Tasks:

- Set up npm organization @vizlint

- Configure package.json for npm publish (files, main, types, exports)

- Write comprehensive README with each rule documented

- Create recommended and strict presets

- Set up GitHub Actions release workflow (tag → build → publish → GitHub Release)

- Test installation in a fresh Next.js + Tailwind project

Test Cases:

- TEST: npm install @vizlint/eslint-plugin installs successfully

- TEST: Recommended preset enables all 5 rules at 'warn' level

- TEST: Strict preset enables all 5 rules at 'error' level

- TEST: Works with ESLint flat config

- TEST: Works with legacy .eslintrc config

- TEST: VS Code ESLint extension shows Vizlint warnings inline

Sprint 4: Service Launch & .cursorrules

Sprint Goal: Productized service live, .cursorrules and CLAUDE.md templates published, first outreach

Velocity Target: 10 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-009: Productized Service Page

As a potential client (vibe coder / founder), I want to understand and purchase the Vizlint design review service, so that I get my AI-generated UI professionally reviewed

Story Points: 5

Acceptance Criteria:

- Service page at vizlint.dev/service with clear pricing

- Tier 1: One-off audit (€997) — single project review, Loom + written report

- Tier 2: Monthly subscription (€1,497/mo) — 1 active review, 48hr turnaround

- Stripe Checkout integration for payment

- Intake form: GitHub/ZIP link, brief context, deadline preference

- Confirmation email with onboarding instructions

Tasks:

- Design service page in Framer

- Set up Stripe account with product/price IDs

- Create Stripe Checkout session for each tier

- Build intake form (Tally.so or Typeform — no custom form needed)

- Set up confirmation email (Resend or Loops)

- Create delivery template (Loom recording structure + written report format)

Test Cases:

- TEST: Stripe Checkout completes successfully (test mode)

- TEST: Intake form submits and notification received

- TEST: Confirmation email delivered within 60 seconds

- TEST: Service page mobile responsive

VIZ-010: Cursor Rules & CLAUDE.md Templates

As a developer using Cursor or Claude Code, I want pre-built design quality rules for my AI coding environment, so that AI generates better UI from the start and I discover Vizlint

Story Points: 3

Acceptance Criteria:

- .cursor/rules/vizlint-design-quality.mdc published to awesome-cursorrules repo (PR submitted)

- CLAUDE.md template with design quality enforcement instructions published to GitHub

- AGENTS.md template for cross-tool compatibility

- Each template references @vizlint/eslint-plugin for automated validation

- Templates cover: spacing, typography, colors, responsive, component structure

Tasks:

- Write .cursorrules file based on personal Vintor design enforcement experience

- Write CLAUDE.md with checkpoint-gated design quality workflow

- Write AGENTS.md for cross-tool compatibility

- Submit PR to PatrickJS/awesome-cursorrules

- Create standalone GitHub repo: vizlint/design-rules

- Write announcement tweet thread with before/after examples

Test Cases:

- TEST: .cursorrules loads correctly in Cursor IDE

- TEST: CLAUDE.md loads at Claude Code session start

- TEST: Rules produce measurably better UI output in A/B test (manual)

VIZ-011: Launch Outreach Sprint

As a CEO, I want to announce Vizlint to the vibe coding community, so that we get first GitHub stars, npm installs, and service leads

Story Points: 2

Acceptance Criteria:

- Twitter/X announcement thread posted (5-7 tweets with code screenshots)

- Reddit posts on r/ClaudeAI, r/cursor_ai, r/webdev, r/reactjs (separate posts, not spam)

- IndieHackers post with build story

- dev.to article: 'I built a design linter because AI-generated UI drove me crazy'

- Target: 100 GitHub stars, 50 npm installs, 2 service inquiries in first week

Tasks:

- Write Twitter thread with before/after screenshots

- Write Reddit posts tailored to each subreddit's rules and audience

- Write IndieHackers build story

- Write dev.to technical article with real code examples

- Schedule posts across 3 days (don't blast everything at once)

Test Cases:

- TEST: All posts live and links functional

- TEST: GitHub repo accessible and README renders correctly

- TEST: npm install command works from all linked posts

PHASE 2: CORE CLI & DESIGN HEALTH SCORE

Sprints 5–8 (Weeks 5–8)  |  CLI with project-wide analysis, Design Health Score, 10+ rules, service revenue growing

Sprint 5: CLI Foundation & Score Engine

Sprint Goal: vizlint CLI runs, scans project, outputs Design Health Score 0–100

Velocity Target: 13 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-012: CLI: Project Scanner

As a developer, I want to run `npx vizlint scan` and get a project-wide design quality report, so that I know the overall design health of my codebase

Story Points: 8

Acceptance Criteria:

- CLI accepts project directory path (defaults to cwd)

- Discovers all .tsx, .jsx, .vue, .svelte, .html files

- Runs all Vizlint ESLint rules across discovered files

- Outputs summary: total files, total violations, violations by rule, violations by severity

- Supports --format json | text | sarif output

- Exits with code 1 if any 'error' severity violations found (CI-friendly)

- Respects .vizlintrc.json configuration file

Tasks:

- Initialize @vizlint/cli package with Commander.js

- Build file discovery with glob patterns and .vizlintignore support

- Integrate ESLint programmatic API (ESLint class with Vizlint plugin)

- Build report aggregator across all files

- Implement output formatters: text (chalk-colored), JSON, SARIF

- Add exit code logic based on severity thresholds

- Create .vizlintrc.json schema with Zod validation

Test Cases:

- TEST: CLI scans a sample Next.js project and finds known violations

- TEST: JSON output is valid JSON matching defined schema

- TEST: SARIF output validates against SARIF 2.1.0 schema

- TEST: Exit code 1 when errors present, 0 when only warnings

- TEST: .vizlintignore excludes specified patterns

- TEST: --format flag correctly switches output format

VIZ-013: Design Health Score Algorithm

As a developer, I want a single 0–100 Design Health Score for my project, so that I can quickly assess and track design quality over time

Story Points: 5

Acceptance Criteria:

- Score computed from weighted sub-scores: Spacing (20%), Typography (20%), Colors (20%), Responsive (20%), Consistency (20%)

- Each sub-score: 100 - (violations / total_opportunities × 100), clamped to 0–100

- Overall score: weighted average of sub-scores

- Color-coded output: 80–100 Green, 60–79 Yellow, 0–59 Red

- Score saved to .vizlint/history.json for trend tracking

- Pass/fail gate configurable: --min-score 75 exits with code 1 if below

Tasks:

- Define scoring formula with sub-score calculations

- Implement opportunity counting per rule category

- Build weighted average calculator

- Create color-coded terminal output with chalk

- Implement history file with JSON append

- Add --min-score CLI flag

Test Cases:

- TEST: Score is 100 for project with zero violations

- TEST: Score decreases proportionally with violations

- TEST: Weights are configurable in .vizlintrc.json

- TEST: --min-score 75 fails project scoring 70

- TEST: History file appends new entry without overwriting

- TEST: Color output matches threshold ranges

Sprint 6: Rules #6–8 & Framework Agnostic

Sprint Goal: A11y contrast, Vue/Svelte support, rule count reaches 8

Velocity Target: 13 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-014: Rule: a11y-color-contrast

As a developer, I want Vizlint to flag text/background color combinations with insufficient contrast, so that my AI-generated UI meets WCAG AA accessibility standards

Story Points: 5

Acceptance Criteria:

- Rule detects text-{color} + bg-{color} combinations on same element or parent

- Rule calculates WCAG 2.1 contrast ratio (minimum 4.5:1 for normal text, 3:1 for large text)

- Rule maps Tailwind color classes to actual hex values for calculation

- Rule reports contrast ratio and minimum required

Tasks:

- Build Tailwind color-to-hex mapping table (all default colors)

- Implement WCAG contrast ratio calculator

- Build parent-child color inheritance resolver

- Implement large text detection (text-lg and above)

- Write unit tests with known pass/fail color combinations

Test Cases:

- TEST: Flags text-gray-400 on bg-gray-300 (fails AA)

- TEST: Passes text-gray-900 on bg-white (passes AA)

- TEST: Large text threshold correctly applied (3:1 for text-xl+)

- TEST: Custom color tokens resolve correctly

VIZ-015: Framework Agnostic: Vue & Svelte Support

As a Vue or Svelte developer, I want Vizlint to work with my framework, not just React, so that I get the same design quality validation regardless of framework

Story Points: 5

Acceptance Criteria:

- Rules parse Vue SFC <template> blocks

- Rules parse Svelte component class attributes

- Rules handle :class bindings (Vue) and class: directives (Svelte)

- All 8 rules work identically across React, Vue, and Svelte

- Plain HTML class attributes also supported

Tasks:

- Add vue-eslint-parser integration for .vue files

- Add svelte-eslint-parser integration for .svelte files

- Create framework-agnostic class extractor abstraction layer

- Port all rules to use abstraction layer instead of JSX-specific visitors

- Write cross-framework test suite

Test Cases:

- TEST: All 8 rules detect violations in React .tsx files

- TEST: All 8 rules detect violations in Vue .vue files

- TEST: All 8 rules detect violations in Svelte .svelte files

- TEST: All 8 rules detect violations in plain .html files

- TEST: Vue :class dynamic bindings handled correctly

VIZ-016: Rules #7–8: Component Complexity & Missing States

As a developer, I want Vizlint to flag over-complex components and missing UI states, so that my components are maintainable and handle edge cases

Story Points: 3

Acceptance Criteria:

- max-component-lines: Flag single-file components exceeding configurable LOC (default: 300)

- missing-states: Detect form elements without error/disabled state handling (missing aria-invalid, disabled prop)

Tasks:

- Implement line count calculator per component

- Build form element detector (input, select, textarea, button)

- Implement state attribute checker

- Write unit tests

Test Cases:

- TEST: Flags 400-line component (default threshold 300)

- TEST: Does NOT flag 250-line component

- TEST: Flags <input> without aria-invalid handling

- TEST: Passes <input> with proper error state attributes

Sprint 7: CLI Polish & npm v0.3.0

Sprint Goal: Polished CLI output, init command, docs site, npm 0.3.0 with 10 rules

Velocity Target: 13 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-017: CLI: Init Command & Config Wizard

As a developer new to Vizlint, I want to run `npx vizlint init` and get set up in 30 seconds, so that onboarding is frictionless

Story Points: 5

Acceptance Criteria:

- `npx vizlint init` creates .vizlintrc.json with interactive prompts

- Prompts: framework (React/Vue/Svelte/Other), CSS approach (Tailwind/CSS Modules/Other), strictness (recommended/strict/custom)

- Auto-detects framework from package.json if possible

- Adds ESLint plugin to eslint.config.js or .eslintrc with correct config

- Prints next-steps summary with first scan command

Tasks:

- Build interactive CLI wizard with inquirer or @clack/prompts

- Implement framework auto-detection from package.json dependencies

- Create config template generator

- Add ESLint config injection (detect flat vs legacy)

- Write integration test with mock project

Test Cases:

- TEST: Init wizard completes in < 30 seconds for a standard Next.js project

- TEST: Auto-detects React from package.json

- TEST: Generated .vizlintrc.json validates against schema

- TEST: ESLint config correctly modified with Vizlint plugin

VIZ-018: Rules #9–10 & v0.3.0 Release

As a developer, I want two more rules covering dark mode and z-index management, so that common AI-generated anti-patterns are caught

Story Points: 5

Acceptance Criteria:

- dark-mode-coverage: Flag components with bg-* classes that lack dark: variants

- no-arbitrary-zindex: Flag z-[N] arbitrary z-index values, suggest scale (z-10/20/30/40/50)

Tasks:

- Implement dark mode variant scanner

- Implement z-index arbitrary value detector

- Update recommended and strict presets

- Update documentation with all 10 rules

- Publish @vizlint/eslint-plugin@0.3.0 and @vizlint/cli@0.1.0 to npm

Test Cases:

- TEST: Flags bg-blue-500 without dark:bg-blue-700 variant

- TEST: Does NOT flag bg-blue-500 when dark:bg-blue-900 present

- TEST: Flags z-[999] and suggests z-50

- TEST: npm publish succeeds, install works in fresh project

VIZ-019: Documentation Site

As a developer evaluating Vizlint, I want comprehensive docs to understand every rule and configuration option, so that I trust the tool enough to install it

Story Points: 3

Acceptance Criteria:

- Docs at vizlint.dev/docs (Framer subpath or separate Nextra/Fumadocs site)

- Every rule documented: description, rationale, examples (good/bad), configuration

- Getting started guide: install → init → scan → fix

- Configuration reference: .vizlintrc.json full schema

- CI/CD integration guide (GitHub Actions example)

Tasks:

- Set up docs framework (Fumadocs or Nextra)

- Write rule documentation for all 10 rules with code examples

- Write getting started guide

- Write configuration reference

- Deploy to vizlint.dev/docs

Test Cases:

- TEST: Every rule page renders correctly

- TEST: Code examples syntax highlighted

- TEST: Search works across docs

- TEST: Mobile responsive

Sprint 8: Phase 2 Wrap & Business Review

Sprint Goal: Service revenue tracked, metrics baseline, product-market signal assessment

Velocity Target: 8 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-020: Metrics Dashboard (Internal)

As a CEO, I want to track npm downloads, GitHub stars, service revenue, and website traffic, so that I make data-driven decisions about what to build next

Story Points: 3

Acceptance Criteria:

- Weekly metrics tracked: npm downloads, GitHub stars/forks, website visits, service revenue, inquiries

- Simple Notion or Google Sheet dashboard (no over-engineering)

- Week-over-week growth calculated

- Phase 2 business review: Go/No-Go on Phase 3 investment

Tasks:

- Set up npm download tracking (npm-stat.com API)

- Set up GitHub star tracking

- Set up Plausible dashboard review

- Create metrics spreadsheet with weekly entry template

- Write Phase 2 business review document

Test Cases:

- TEST: All metrics sources accessible and reporting data

- TEST: Business review document answers: Are we on track for revenue? Should we pivot?

VIZ-021: Community Feedback Integration

As a developer who filed a GitHub issue, I want my feedback to be acknowledged and addressed, so that I trust Vizlint as an actively maintained project

Story Points: 5

Acceptance Criteria:

- All GitHub issues triaged within 48 hours

- Top-requested rules identified for Phase 3

- Bug fixes shipped in patch releases (0.3.x)

- Discord or GitHub Discussions set up for community

Tasks:

- Triage all open GitHub issues

- Categorize: bugs, feature requests, rule requests

- Fix critical bugs, release 0.3.x patches

- Set up GitHub Discussions with categories: Rules, Configuration, Show & Tell

- Write 'What's Next' roadmap post

Test Cases:

- TEST: All issues have responses

- TEST: Critical bugs fixed and released

- TEST: Community channel accessible and monitored

PHASE 3: MCP SERVER & CI/CD INTEGRATION

Sprints 9–12 (Weeks 9–12)  |  Real-time design quality feedback in Cursor/Claude Code, GitHub PR integration, Design Health in CI pipelines

Sprint 9: MCP Server Core

Sprint Goal: MCP server runs locally, provides analyze_file and suggest_fixes tools to Claude Code and Cursor

Velocity Target: 13 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-022: MCP Server: Core Architecture

As a developer using Claude Code, I want real-time design quality feedback as I code, so that violations are caught at generation time, not review time

Story Points: 8

Acceptance Criteria:

- MCP server exposes 3 tools: analyze_file, analyze_project, suggest_fixes

- Server communicates via stdio (JSON-RPC 2.0) — zero network calls

- analyze_file: accepts file path, returns violations + Design Health sub-score

- suggest_fixes: accepts violation, returns specific code fix suggestion

- Server starts in < 2 seconds

- Only structured analysis results sent to LLM — never raw source code

Tasks:

- Initialize @vizlint/mcp package

- Implement MCP server using @modelcontextprotocol/sdk StdioServerTransport

- Create tool schemas for analyze_file, analyze_project, suggest_fixes

- Integrate ESLint programmatic API for file analysis

- Build fix suggestion generator from ESLint autofix data

- Write integration tests with mock MCP client

- Create installation instructions for claude_desktop_config.json and Cursor settings

Test Cases:

- TEST: MCP server starts and responds to initialize handshake

- TEST: analyze_file returns correct violations for known-bad file

- TEST: analyze_file returns clean result for known-good file

- TEST: suggest_fixes returns actionable code suggestion

- TEST: No file content appears in MCP responses (privacy check)

- TEST: Server startup time < 2 seconds

VIZ-023: MCP Server: Cursor & Claude Code Integration

As a developer, I want to add Vizlint to my Cursor or Claude Code environment in one command, so that design quality feedback appears automatically during AI code generation

Story Points: 5

Acceptance Criteria:

- npx @vizlint/mcp install auto-configures Cursor/Claude Code MCP settings

- Works with both Cursor MCP and Claude Desktop config

- Clear documentation with screenshots of setup process

- Uninstall command to cleanly remove configuration

Tasks:

- Build install CLI that detects Cursor vs Claude Desktop config locations

- Implement config injection (add server to mcp_servers list)

- Build uninstall command

- Write setup guide with screenshots

- Test on macOS, Linux, and Windows paths

Test Cases:

- TEST: Install command correctly modifies Cursor config on macOS

- TEST: Install command correctly modifies claude_desktop_config.json

- TEST: Uninstall cleanly removes Vizlint from config

- TEST: Server appears in Cursor/Claude Code MCP tool list after install

Sprint 10: GitHub PR Integration

Sprint Goal: Design Health comments appear on GitHub PRs via GitHub Action

Velocity Target: 13 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-024: GitHub Action: PR Design Review

As a team lead, I want automatic design quality reviews on every PR, so that design drift is caught before merge, not after deploy

Story Points: 8

Acceptance Criteria:

- GitHub Action runs vizlint scan on changed files in PR

- Posts PR comment with: Design Health Score delta, top violations, inline code suggestions

- Comment updates on subsequent pushes (no duplicate comments)

- Configurable: fail PR check if score drops below threshold

- Action published to GitHub Marketplace

Tasks:

- Create GitHub Action (composite action with Node.js)

- Build PR diff analyzer to identify changed frontend files

- Implement GitHub API comment posting with markdown formatting

- Add comment deduplication logic (find-and-update pattern)

- Add check status reporting (pass/fail based on --min-score)

- Create action.yml with documented inputs

- Write setup guide for teams

- Publish to GitHub Marketplace

Test Cases:

- TEST: Action runs on PR creation

- TEST: Comment contains Design Health Score and violation summary

- TEST: Subsequent pushes update existing comment

- TEST: Check fails when score below configured threshold

- TEST: Action handles projects with zero frontend files gracefully

- TEST: Action completes within 60 seconds for a 100-file project

VIZ-025: Rule Expansion: 12–15 Rules Total

As a developer, I want Vizlint to catch more design anti-patterns, so that comprehensive design quality coverage

Story Points: 5

Acceptance Criteria:

- no-inline-styles: Flag style={{}} attributes — suggest Tailwind classes

- consistent-border-radius: Detect mixed rounded-* values across same-type components

- image-alt-text: Flag <img> without alt attribute or with alt=''

- no-magic-numbers-layout: Flag hardcoded numbers in grid/flex layout (cols-[N], basis-[Npx])

- total rule count reaches 14–15

Tasks:

- Implement 4 new rules following established patterns

- Add to recommended and strict presets

- Write documentation for each rule

- Update npm packages to 0.5.0

Test Cases:

- TEST: Each new rule detects violations and provides suggestions

- TEST: Each new rule has 0 false positives on a clean project

- TEST: Documentation renders correctly

Sprint 11: Paid CLI Tier & Licensing

Sprint Goal: Free vs Pro CLI differentiation, license key system, Stripe subscription

Velocity Target: 13 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-026: Paid CLI: Pro Features & License Key

As a developer wanting advanced features, I want to unlock Pro CLI features with a subscription, so that I get project-wide analysis, CI integration, and team configs

Story Points: 8

Acceptance Criteria:

- Free CLI: scan single file, 5 core rules, text output only

- Pro CLI (€19/mo): scan full project, all rules, JSON/SARIF output, Design Health Score, history tracking, --min-score gate

- License key validation: offline-first (JWT with expiry), online check weekly

- License key set via VIZLINT_LICENSE env var or vizlint auth command

- Stripe subscription → license key delivery via email

- 14-day free trial (no credit card)

Tasks:

- Implement license key generation (JWT signed with RS256)

- Build license validation middleware in CLI (check before Pro features)

- Create Stripe subscription product with webhook for key delivery

- Build vizlint auth login/logout commands

- Implement trial logic (14 days from first use timestamp)

- Create pricing page on vizlint.dev

Test Cases:

- TEST: Free tier limits enforced (single file, 5 rules)

- TEST: Valid license key unlocks all features

- TEST: Expired license key falls back to free tier with warning

- TEST: Offline validation works with valid JWT for up to 30 days

- TEST: Stripe webhook delivers license key via email

- TEST: Trial expires after 14 days

VIZ-027: Product Hunt Launch Preparation

As a CEO, I want a polished Product Hunt launch that maximizes Day 1 traction, so that Vizlint reaches 1,000+ developers on launch day

Story Points: 5

Acceptance Criteria:

- Product Hunt listing prepared: tagline, description, 5 screenshots, maker video (< 2 min)

- Launch day plan: posting time, HN cross-post, Twitter thread, Reddit posts

- Teaser campaign: 2 weeks of 'coming soon' posts showing design quality insights

- Email list of early users/stars notified on launch day

Tasks:

- Record 2-minute demo video showing Vizlint in action

- Take 5 high-quality screenshots (CLI output, VS Code integration, before/after)

- Write Product Hunt listing copy

- Prepare HN Show HN post

- Schedule launch for Tuesday (highest PH traffic day)

- Build simple email list capture on vizlint.dev

Test Cases:

- TEST: All launch assets reviewed and approved (CEO hat)

- TEST: Demo video is compelling and under 2 minutes

- TEST: All links in listing are functional

Sprint 12: Launch Week & Phase 3 Review

Sprint Goal: Product Hunt launch, HN post, metrics assessment, Phase 4 Go/No-Go

Velocity Target: 8 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-028: Product Hunt & Hacker News Launch

As a CEO, I want to execute a coordinated launch across Product Hunt, Hacker News, and social channels, so that Vizlint gets maximum exposure to the developer community

Story Points: 3

Acceptance Criteria:

- Product Hunt submitted and ranked (target: Top 5 of the day)

- Hacker News Show HN posted

- Twitter thread live with 10+ retweets

- Reddit posts on 3+ subreddits

- Target: 500 npm installs, 300 GitHub stars, 5 Pro trial signups in launch week

Tasks:

- Execute launch day plan

- Respond to every PH comment within 1 hour

- Respond to HN comments

- Monitor and engage Reddit posts

- Track metrics hourly on launch day

Test Cases:

- TEST: All channels posted and links functional

- TEST: Response time to comments < 1 hour

- TEST: Metrics tracked and documented

VIZ-029: Phase 3 Business Review

As a McKinsey consultant, I want to evaluate Vizlint's traction and decide Phase 4 investment, so that we make a data-driven Go/No-Go decision

Story Points: 5

Acceptance Criteria:

- Metrics reviewed: npm downloads, GitHub stars, Pro trials, service revenue, website traffic, CAC

- Revenue assessment: current MRR vs projection

- Product-market fit signals: retention, feature requests, organic mentions

- Go/No-Go decision documented with rationale

- Phase 4 scope adjusted based on learnings

Tasks:

- Compile all metrics into review document

- Calculate unit economics: CAC, LTV estimate, payback period

- Assess PMF signals: are users coming back? Are they telling others?

- Write Go/No-Go recommendation with supporting data

- Adjust Phase 4 backlog based on user feedback priorities

Test Cases:

- TEST: Review document answers all McKinsey questions with data

- TEST: Decision is documented and actionable

PHASE 4: DASHBOARD, TEAMS & SCALE

Sprints 13–16 (Weeks 13–16)  |  Web dashboard for teams, Design Health trends, team configs, enterprise readiness

Sprint 13: Team Dashboard MVP

Sprint Goal: Web dashboard showing Design Health Score trends per project

Velocity Target: 13 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-030: Dashboard: Project Overview

As a team lead, I want to see Design Health Score trends for my project in a web dashboard, so that I can track design quality improvement over time

Story Points: 8

Acceptance Criteria:

- Dashboard at app.vizlint.dev behind auth (GitHub OAuth)

- Project creation: connect GitHub repo

- Design Health Score trend chart (last 30 days)

- Violation breakdown by rule category (pie chart)

- Most violated files list (top 10 hotspots)

- Score comparison: current vs last week vs last month

Tasks:

- Set up Next.js 15 app with Tailwind + shadcn/ui

- Implement GitHub OAuth via NextAuth.js

- Create Supabase database schema: projects, scans, violations

- Build API routes for project CRUD and scan data ingestion

- Build Dashboard page with Recharts trend chart

- Build violation breakdown with category pie chart

- Implement hotspot file ranking

- Deploy to Vercel

Test Cases:

- TEST: GitHub OAuth login/logout works

- TEST: Project connects to GitHub repo

- TEST: Score trend chart renders with historical data

- TEST: Dashboard loads in < 3 seconds

- TEST: Mobile responsive layout

VIZ-031: CLI → Dashboard Data Pipeline

As a developer running Vizlint in CI, I want scan results to automatically appear in the team dashboard, so that no manual data entry — CI/CD is the source of truth

Story Points: 5

Acceptance Criteria:

- vizlint scan --report sends results to Vizlint API (opt-in, requires auth token)

- Only aggregated metrics sent (score, violation counts) — never source code

- Data pipeline encrypted in transit (HTTPS) and at rest (Supabase encryption)

- Clear privacy documentation: what is sent, what is not, how to opt out

Tasks:

- Create API endpoint: POST /api/scans with auth token validation

- Add --report flag to CLI that sends aggregated results

- Implement auth token generation in dashboard

- Write privacy documentation page

- Add opt-in confirmation prompt on first --report use

Test Cases:

- TEST: Scan results appear in dashboard within 30 seconds of CI run

- TEST: No source code appears in API payloads (privacy audit)

- TEST: Invalid auth token returns 401

- TEST: --report without auth token shows setup instructions

Sprint 14: Team Features & Pricing

Sprint Goal: Team subscription tier, shared rule configs, member management

Velocity Target: 13 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-032: Team Subscription & Member Management

As a team lead, I want to subscribe my team and manage member access, so that everyone on my team uses the same Vizlint configuration

Story Points: 8

Acceptance Criteria:

- Team tier: €29/user/month (minimum 3 users)

- Team creation with invite-by-email

- Shared .vizlintrc.json synced from dashboard to all team members

- Team-level Design Health Score (aggregate across all team projects)

- Admin/member role distinction

Tasks:

- Implement team CRUD in Supabase (teams, team_members, invitations)

- Build team settings page in dashboard

- Create invitation flow with email notifications

- Implement shared config sync (API endpoint team members pull from)

- Add team aggregate score calculation

- Create Stripe team subscription with per-seat billing

Test Cases:

- TEST: Team creation and member invitation works

- TEST: Shared config syncs to team members' CLI

- TEST: Team aggregate score calculated correctly

- TEST: Stripe billing updates when team size changes

- TEST: Admin can remove members

VIZ-033: Custom Design System Rules

As a design-conscious team, I want to define custom rules matching our specific design system, so that Vizlint enforces our brand guidelines, not just generic best practices

Story Points: 5

Acceptance Criteria:

- Custom color token definitions (brand-primary: #1A5276, etc.)

- Custom spacing scale override

- Custom typography scale override

- Custom component naming conventions

- Custom rules definable in .vizlintrc.json

Tasks:

- Extend .vizlintrc.json schema with designSystem section

- Implement custom color token resolution in all color rules

- Implement custom spacing scale in spacing rules

- Implement custom type scale in typography rules

- Write guide: 'Configuring Vizlint for Your Design System'

Test Cases:

- TEST: Custom brand-primary color recognized and enforced

- TEST: Custom 8px spacing scale enforced instead of Tailwind default

- TEST: Custom type scale enforced

- TEST: Configuration errors produce clear error messages

Sprint 15: Security Hardening & Enterprise Prep

Sprint Goal: Security audit, rate limiting, audit logging, enterprise feature flags

Velocity Target: 10 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-034: Security Hardening

As a CTO evaluating Vizlint for enterprise, I want confidence that Vizlint is secure and won't expose our code, so that I approve Vizlint for company-wide use

Story Points: 8

Acceptance Criteria:

- Dependency audit: no known CVEs in production dependencies

- API rate limiting: 100 requests/minute per auth token

- Input validation on all API endpoints (Zod schemas)

- CORS configured: only app.vizlint.dev origin

- Auth tokens hashed in database (never stored plaintext)

- Audit log: all API access logged with timestamp, action, user

- Security page at vizlint.dev/security documenting practices

- Responsible disclosure policy published

Tasks:

- Run npm audit and fix all vulnerabilities

- Implement rate limiting middleware (upstash/ratelimit or custom)

- Add Zod validation to all API route handlers

- Configure CORS headers

- Implement auth token hashing (argon2)

- Build audit log table and write middleware

- Write security documentation page

- Create security@vizlint.dev email for disclosures

Test Cases:

- TEST: npm audit returns 0 vulnerabilities

- TEST: Rate limit triggers at 101st request in 60 seconds

- TEST: Invalid API input returns 400 with clear error

- TEST: CORS blocks requests from unauthorized origins

- TEST: Auth tokens not visible in database (only hashes)

- TEST: Audit log records all API access

VIZ-035: Enterprise Feature Flags

As a enterprise buyer, I want SSO, audit exports, and SLA guarantees, so that Vizlint meets our procurement requirements

Story Points: 2

Acceptance Criteria:

- Feature flag system for gating enterprise features

- SSO placeholder (SAML/OIDC integration spec documented, not yet built)

- Audit log CSV export for compliance teams

- SLA documentation: 99.9% API uptime target

- Enterprise pricing page: 'Contact us' with Calendly link

Tasks:

- Implement feature flag system (simple JSON config, no third-party service)

- Write SSO integration spec document

- Build audit log CSV export endpoint

- Write SLA documentation

- Create enterprise pricing page with contact form

Test Cases:

- TEST: Feature flags correctly gate enterprise features

- TEST: CSV export contains correct audit data

- TEST: Enterprise contact form submits notification

Sprint 16: V1.0 Release & Business Plan

Sprint Goal: Production release, complete documentation, revenue targets, 6-month roadmap

Velocity Target: 8 story points

────────────────────────────────────────────────────────────────────────────────

VIZ-036: V1.0 Release

As a developer, I want to use a stable, production-ready version of Vizlint, so that I trust Vizlint for production CI/CD pipelines

Story Points: 5

Acceptance Criteria:

- @vizlint/eslint-plugin@1.0.0 published with 15+ rules

- @vizlint/cli@1.0.0 published with full feature set

- @vizlint/mcp@1.0.0 published with Cursor + Claude Code support

- Semantic versioning commitment: no breaking changes in 1.x

- Migration guide from 0.x to 1.0

- CHANGELOG documenting all changes since 0.1.0

Tasks:

- Audit all public APIs for stability (no experimental exports)

- Write migration guide

- Update all documentation to v1.0

- Create GitHub Release with comprehensive release notes

- Announce on all channels

- Submit to ESLint community plugins list

Test Cases:

- TEST: All packages install cleanly from npm

- TEST: All rules pass against test suite (100% green)

- TEST: Migration guide tested with a 0.x → 1.0 upgrade

- TEST: No TypeScript errors in any package

VIZ-037: 6-Month Business Plan

As a CEO, I want a clear business plan for the next 6 months, so that I know exactly what to build, how to grow, and when to hire

Story Points: 3

Acceptance Criteria:

- Revenue targets: Month 4–6 projections based on current trajectory

- Product roadmap: v1.1–v2.0 feature priorities based on user feedback

- Hiring plan: when to hire first contractor/employee (revenue threshold)

- Marketing plan: content calendar, conference talks, partnership outreach

- Competitive monitoring: track Figma, Vercel, Cursor moves in design quality

- Exit scenarios documented: bootstrap to profitability vs raise seed

Tasks:

- Compile all metrics into trajectory model

- Write product roadmap based on GitHub issues and user interviews

- Define hiring threshold (e.g., €10K MRR = first contractor)

- Create content calendar for next 3 months

- Write competitive watch brief

- Document strategic options

Test Cases:

- TEST: Business plan reviewed by McKinsey hat — all numbers justified

- TEST: Roadmap prioritized by user demand data

- TEST: Plan is actionable, not aspirational

# Release Milestones & Revenue Targets

| Milestone | When | Release | What Ships | Targets |
| --- | --- | --- | --- | --- |
| End of Sprint 3 | Week 3 | @vizlint/eslint-plugin@0.1.0 | 5 rules on npm | 50 npm installs, 30 GitHub stars |
| End of Sprint 4 | Week 4 | Service Launch | Productized service live | €0–2K MRR (service) |
| End of Sprint 7 | Week 7 | @vizlint/eslint-plugin@0.3.0 + CLI | 10 rules, CLI with Design Health Score | 200 npm installs, 100 stars, €2–5K MRR |
| End of Sprint 11 | Week 11 | Pro CLI + MCP + GitHub Action | Paid tier live, MCP server, PR integration | 500 installs, 300 stars, €3–8K MRR |
| End of Sprint 12 | Week 12 | Product Hunt Launch | Public launch across all channels | 1,000 installs, 500 stars, 10 Pro trials |
| End of Sprint 16 | Week 16 | V1.0 Stable Release | Production-ready, dashboard, teams | 2,000 installs, 800 stars, €5–15K MRR |

## Total Story Points by Phase

Phase 1 (Sprints 1–4): 49 story points — Foundation, 5 rules, service, landing page, launch outreach

Phase 2 (Sprints 5–8): 47 story points — CLI, Design Health Score, 10 rules, docs, framework agnostic

Phase 3 (Sprints 9–12): 47 story points — MCP server, GitHub Action, Pro tier, Product Hunt launch

Phase 4 (Sprints 13–16): 44 story points — Dashboard, teams, security, v1.0, business plan

Grand Total: 187 story points across 16 sprints (avg 11.7 per sprint)